## Slide 1: Ensembl Migration to EBI

## Slide 2: Background: 8 work packages
WP1/2: Migration of Ensembl 82 Archive and all other archives
WP3: Ensembl FTP
WP4: Ensembl Public MySQL
WP5/6: Production: All content teams
WP7: Live Ensembl Websites and services
WP8: External communications

## Slide 3: https://avullo.github.io/ensembl-migration-pm

## Slide 4: Migration Timeline: Q1 2017
Oct 16
Dec16
e87
Mar 17
e88
Sept 16
e86
To be capable of running all public services and production processes at EBI by release 88

## Slide 5: Migration Timeline: Q4 2016
Oct 16
Dec16
e87
Mar 17
e88
Sept 16
e86
Archives at EBI, web infrastructure ready for live site, production run confirmed

## Slide 6: Migration Timeline: Oct 2016
Migration of Ensembl DB, Ensembl FTP, RT, production environment ready
Oct 16
Dec16
e87
Mar 17
e88
Sept 16
e86

## Slide 7: Migration Timeline: Sept 2016
Production environment ready for use, hardware available, MySQL servers ready
Oct 16
Dec16
e87
Mar 17
e88
Sept 16
e86

## Slide 8: Progress
WP1-2: Archives
  Hosting archives on HX Embassy
  All archives have been uploaded using shadowland
  e82 successfully deployed
  e54 and e67 images hosted as proof of concept
WP3: FTP
  All FTP transferred to EBI warehouse
  Server being setup
WP4: Public MySQL
  Transfer done an awaiting hardware (MySQL 4 issues)

## Slide 9: Progress
WP5-6: Production
  Software environment deployed for testing RHEL7
  /nfs/software/ensembl
  RHEL6 testing aborted
  MySQL servers requested (32GB 4 cores and 64GB 8 cores for staging)
  Lustre available at EBI for use
WP7: Services
  Hardware on site for web; awaiting TSC meeting to define topology
  Investigating co-hosting REST with EBI based websites
  CVS at Sanger turned off with archive at EBI available
Notes: EG web have requested a read only git migration of a CVS repo

## Slide 10: Progress
WP8: External communication
  Bought in external consultancy to migrate RT from Best Practical
  Migration slated for Mid-October (17th-21st)
  Downtime expected to be minimal
  Delayed due to numbers of reasons including data centre shutdown
  Dev and announce lists being discussed with Sanger systems

## Slide 11: Next Steps
Get hardware to everyone
Decide on the website topology
Get running as many processes/services/tools at EBI as possible