e! migration
The Great (WTSI) Escape
Alessandro Vullo
Ensembl Data Review
Oct 10 2016
EMBL – European Bioinformatics Institute
Wellcome Trust Genome Campus
Hinxton, Cambridge, CB10 1SD, UK

---
Objective(s)
assert(e_sanger_footprint == 0) if date =~ /Mar 2017/
  - be as much transparent to the public as possible
  - maintenance of public face is of paramount importance: public web sites (UK/AWS), MySQL access, mailing lists
  - production processes are important but secondary

---
The Plan (Summary)
- Split e! into three distinct groups, migrate each of these in turn
- Migrate
  1. public archive services (archives, FTP)/public web presence
  2. release production processes
  3. processes outside of release cycle
[Speaker Notes: Expertise from Ensembl Genomes, who run many Ensembl pipelines already at EBI, will be leveraged. Early migration of non-release linked resources such as our archive and FTP site will ensure EBI is aware of our requirements and expose issues early. Maintenance of our public face is of paramount importance.]

---
Ensembl Flow
[Speaker Notes: How to think about e!? At the simplest level you distinguish two major areas: production/data release (web/FTP/MySQL) + helpdesk Ensembl operates a 4 to 5 release policy per year resulting in 9 releases over 2 years. This roughly means a production cycle and data release once every 11 weeks. During this production cycle (represented by Group 2 in Figure 1) data is delivered from content teams, processed by other content teams and then finally delivered to a staging database and file system depending on the data format. Once fully collated this data is delivered to our public distribution channels (represented by Group 3 in Figure 1) and mostly takes the form of 19 websites: one delivering the latest release and 16 delivering an archive release. The final Group represents data that is produced out of cycle and awaits the next Ensembl release to schedule further processing. For example a gene build, the process of annotating a genome with transcription models, is rarely released publicly without the addition of cross references and mappings between genome versions. The Vega website and data production tasks are the responsibility of the Ensembl webteam. This is generally done on a much smaller scale than, and at different times to, Ensembl. It does present a particular challenge in the need for frequent updates to data outside of the release cycle.]

---
Sanger Footprint
- ~330TB storage (production, web live/archive servers)
  - DDN 103TB
  - Nexsan 228TB
- ~110 machines: ? Cores/? RAM
  - ~30 production DB servers (BM)
  - ~80 web related servers (~50 BM/~30VMs)
  - RAM:
    - 1.1TB production
    - ? web (0.7TB DB, 1.7TB live/tools, ? archives)
  - Cores: ?
- Farm processing
  - ? CPU years
  - ? TB clustered filesystem (lustre)
[Speaker Notes: The majority of Ensembl servers are bare metal. The exception are our archive web servers, search engines and private data (data sets which cannot be released externally) database servers which are VM based.]

---
3, 2, 1 go!
- September 2015: commence
- <February 2016: Ok-ish, slow pace
  - initial discussions with EBI/Sanger groups
  - AV takes on PM role (Jan)
  - identify tech requirements in more details
    - benchmarking Sanger machines: mainly storage, no real gold/silver/bronze conclusions
    - DB meetings (move data across, back ups, MySQL versions)
- Feb 2016: there's an HX shutdown, bang!

---
Hinxton shutdown
- When
- What
- How
- Consequences for e! (state at that time at that moment)
- Planned strategy

---
Disaster Recovery Architecture
- In conjuction with TSC
- Ask Steve the details

---
Funding

---
Overall
- State: 45%?
- Survived shutdown (?)
  - HW resources mostly allocated (budget employed, accountancy wizardry)
  - Networking infrastructure to support data transfer
- CVS/RT migration completed (?)
- Archives/FTP/public MySQL on the go (thanks to shadowland)
- Web infrastructure work started (moved accounts/tools?/sessions?)
- Production:
  - HW requisitioned (DB servers, FARM, data storage)
  - software environment installed (almost stabilised), pipelines tested

---
Public Archive Services
- e! maintains archive of past releases (3ys)
  - past 13 releases (includes NCBI36 e!54), e.g. may2009.archive.ensembl.org
  - 2 key species archive: NCBI m37 (e67), Zv8 (e59)
- Objective: migrate autumn/fall 2016
[Speaker Notes: In the next WT funding cycle this will grow to 5 years of archives. We will aim to migrate our public archive services first followed by our public web presence (group 3). Early migration of non-release linked resources such as our archive and FTP site will ensure EBI is aware of our requirements and expose issues early.]

---
WTSI set up

---
WTSI set up (2)
- 28 servers: ? Cores/? RAM/? storage
  - 15 releases archive (past 13 releases plus 2 key species plus GRCh37): 18 VMs, ? Cores/? GB RAM/Storage?
  - Each archive site accompanied by search server: 15VMs, ? Cores /225GB RAM/7TB DDN
    - 8 Solr e!>=73
    - 5 Lucene
    - 1 exalead
  - Archives/GRCh37 DB-Solr servers: ? Cores/? RAM/? Storage (BM)
  - NFS? Web data
  - Shared user DB with live web
  - Hosted on VMWare platform

---
Archives Migration Plan
- Spring 2016 – Migrate 82 archive (WP1) (not full fledge migration, need completion of WP2 before run)
  - request image
  - requisition DB servers (data hosting, user sessions, mart)/NFS server
  - copy release data from EBI mirror
  - upload WTSI images (web/solr search) – critical

---
Archives Migration Plan (2)
- Autumn 2016 – Host all archives on Embassy (why?) (WP2)
  - EBI to Embassy VPN (shared accounts DB)
  - deploy service monitoring infrastructure
  - control procedures/load balancer
  - transfer stats

---
Milestones
- State: 40% done
- Jan 2016: 1%
  - request 82 VMs
  - set up Embassy space
- March-May 2016: 5%
  - upload 82 images (ovftool from Sanger farm) and data (EBI mirror)
  - main DB/Mart/NFS servers set up, use main as replacement accounts DB
- June 2016: 10%
  - infrastructure developments: networking (route trafficking), security
- July 2016: 25%
  - testing transfer procedure for all archives (need to pick right ovftool version to bypass some obscure authentication problems)
  - shadowland ready for data transferring
  - upload/testing e64/67 images (proof of concept)
- August 2016: 40%
  - debugging VM boot problems
  - moving data (ensembldb) to EBI
  - requisition enough storage: 80TB
- Current rate: 5%/month, will end July 2016, but most of remaining are repeatable steps, infrastructure is in place, data transfer in place (need to fix couple of glitches and should be ok)

---
FTP
- 32TB disk hosted on FTP, HTTP(S) and Rsync
- require to be able to sync, on a per release basis, all data held in the Ensembl FTP site onto a co-mirror hosted in HH
- EBI set up (covered by extra purchase)
- Objective: migrate by end 2016

---
FTP Migration Plan
- Discuss it or move directly to web?
- Can bypass, but write it down for records

---
Milestones
- State: ?%
- January 2016?:
  - request space (not available, need money)
- March 2016?:
  - data transfer access point/ftp test server available
- August 2016?:
  - E! purchase does not cover FTP space, need extra purchase? Elaborate

---
Public Web Presence
- Dialogue with Steve to figure out the whole infrastructure and describe it in a simple but detailed way
- Storage, compute (web/farm nodes), filesystems

---
Production (including genebuilders)
- Filesystems
- Storage
- Farm
  - Sanger set up (ask?)
  - EBI set up (Asier talk)

---
Acknowledgements
- Mag, Daniel
  - supportive and guiding in difficult moments
- Andy, Steve, Dan Ss
  - the underlying heroes, competent gentlemen
- Migration champions
- Group leaders
- Everybody in e!