Ensembl migration
The great (WTSI) escape
Alessandro Vullo
Ensembl Data Review
Oct 17 2016
EMBL – European Bioinformatics Institute
Wellcome Trust Genome Campus
Hinxton, Cambridge, CB10 1SD, UK

---
Objective(s)
assert(e_sanger_footprint == 0) if date =~ /Mar 2017/
  - maintenance of public face is of paramount importance: public web sites (HX/AWS), FTP/MySQL access, RT/mailing lists
  - production processes are important as well

---
The Plan (Summary)
Migrate 3 groups in turn
  1. public archive services (archives, FTP/MySQL)/web presence (HX)
  2. release production processes
  3. processes outside of release cycle
[Speaker Notes: Expertise from Ensembl Genomes, who run many Ensembl pipelines already at EBI, will be leveraged. Early migration of non-release linked resources such as our archive and FTP site will ensure EBI is aware of our requirements and expose issues early. Maintenance of our public face is of paramount importance.]

---
Ensembl Flow
[Speaker Notes: How to think about e!? At the simplest level you distinguish two major areas: production/data release (web/FTP/MySQL) + helpdesk Ensembl operates a 4/5 release policy per year resulting in 9 releases over 2 years. This roughly means a production cycle and data release once every 11 weeks. During this production cycle (represented by Group 2 in Figure 1) data is delivered from content teams, processed by other content teams and then finally delivered to a staging database and file system depending on the data format. Once fully collated this data is delivered to our public distribution channels (represented by Group 3 in Figure 1) and mostly takes the form of 19 websites: one delivering the latest release and 16 delivering an archive release. The final Group represents data that is produced out of cycle and awaits the next Ensembl release to schedule further processing. For example a gene build, the process of annotating a genome with transcription models, is rarely released publicly without the addition of cross references and mappings between genome versions. The Vega website and data production tasks are the responsibility of the Ensembl webteam. This is generally done on a much smaller scale than, and at different times to, Ensembl. It does present a particular challenge in the need for frequent updates to data outside of the release cycle.]

---
Sanger Footprint
- ~330TB storage (production, web live/archive servers)
  - DDN SAN 103TB
  - Nexsan 228TB
- 125 servers: ~1300 Cores/~3.2TB RAM
  - 29 DB production
  - 33 DB web & public services
  - 63 web sites (incl. archives)/search/tools
- Farm processing
  - ~500 CPU yrs (2015)
  - ~45 TB clustered filesystem (lustre)
  - ~200TB NFS storage areas (warehouse)
[Speaker Notes: The majority of Ensembl servers are bare metal. The exception are our archive web servers, search engines and private data (data sets which cannot be released externally) database servers which are VM based.]

---
3, 2, 1 go!
- September 2015: commence
- <February 2016: Ok-ish, slow pace
  - initial discussions with EBI/Sanger groups
  - AV takes on PM role (Jan)
  - identify tech requirements in more details
    - benchmarking Sanger machines: mainly storage
    - DB meetings (move data across, back ups, MySQL versions)
- Feb 2016: shutdown in HX, bang!

---
Hinxton Data Centre Shutdown
- 26-30 Aug 2016, power cycle (every 5 yrs), electrical maintenance
- Impact: internal/external services HX hosted
- Major consequences for e!

---
Oh no, suicidal!
- Some production/web db servers on potentially faulty IBM blades (50% chance to recover)
- No strategy other than Sanger/IBM try to fix them
- Sanger suggests to migrate away from this HW ASAP!
- Main concerns:
  - managing release
  - guarantee public services

---
We need HW soon!
- Cope with shutdown, provision in time to advance plan implementation
- Need ~£400K hypervisors/storage
- Have ~£250K (e! overhang budget)
- Will:
  - buy in on e! budget (£150K shortfall)
  - EBI pre-award push shortfall into
  - WT award in Oct charged EMBL pre-award

---
Strategy (web)
- user/tools/hive DBs migrate to EBI asap
- shadowland(?!) connects web/archives to DBs
- EBI-AWS VPN for mirrors
- Sanger blades:
  - web servers OK
  - species/mart/other DBs are suicidal, use Solr servers as fallback

---
Web & VPN/shadowland

---
Strategy (production)
- production remains at Sanger
  - e!86 processes finish before (Aug 22)
- staging servers backed up
- teams make sure not to use suicidal HW
- suicidal servers flagged for attention
  - source suitable replacements if pbs

---
What Happened
- A number of VMWare VMs have come back with different IPs
- Pb with new Solr servers, java process stopping e! tomcat
- A number of the IBM blades have not come back and some others had trouble with their storage
  - new system board and more memory
  - all blades back and serviceable (Aug 31 evening)

---
Background
- WP1-2: e! archives
- WP3: e! FTP
- WP4: e! public MySQL
- WP5-6: all content teams
- WP7: live e! websites and services
- WP8: outreach
[Speaker Notes: So, after the shutdown, back to normal business. How is this migration organised? It's structured around 8 Wps, well in reality we have 10 Wps, but 10 is directly linked to WP5-6 and 9 is related to the migration of Vega. I'm gonna make a short introduction to each one, with an explanation of where we are and what we've done so far.]

---
Public Archive Services
- e! maintains archives (3yrs)
  - past 13 (includes NCBI36 e!54), e.g. may2009.archive.ensembl.org
  - 2 key species archive: NCBI m37 (e67), Zv8 (e59)?
- Objective: migrate autumn 2016
[Speaker Notes: e! maintains an archive of 15 releases representing 13 releases of the past 3 yrs, and two key species archives. In the new WT funding cycle this will grow to 5 years of archives.]

---
WTSI set up
[Speaker Notes: The archives are provided by VMs hosted on the VMWare virtualisation platform at Sanger. Each archive site has an accompanying search server. Releases prior to Ensembl 73 (September 2013) use Lucene as a base. Archives from 73 onwards now use Solr. Finally one old archive, NCBI36 (May 2009), requires an Exalead search index. Yellow means a VM, blue are long-term archives and red are bare metal servers. Purple represents the long term database.]

---
WTSI set up (2)
- 28 servers: ? Cores/? RAM/? storage
  - 15 releases archive (past 13 releases plus 2 key species plus GRCh37): 18 VMs, ? Cores/? GB RAM/Storage?
  - Each archive site accompanied by search server: 15VMs, ? Cores /225GB RAM/7TB DDN
    - 8 Solr e!>=73
    - 5 Lucene
    - 1 exalead
  - Archives/GRCh37 DB-Solr servers: ? Cores/? RAM/? Storage (BM)
  - NFS? Web data
  - Shared user DB with live web
  - Hosted on VMWare virtualisation platform

---
Archives Migration Plan
- Host archives on VMWare Embassy
- Spring 2016 - Migrate e!82 archive (WP1)
  - request image
  - requisition DB servers (data hosting, user sessions, mart)/NFS server
  - copy release data from EBI mirror
  - upload WTSI images (web/solr search) – critical

---
Archives Migration Plan (2)
- Autumn 2016 – Host all archives on Embassy (WP2)
  - transfer all images
  - EBI-Embassy VPN (shared accounts DB)
  - deploy service monitoring infrastructure
  - control procedures/load balancer
  - transfer stats
  - DNS redirect
  - SOP to create archive at EBI

---
Milestones (State: 60% done)
- Jan '16: 1%
  - request 82 VMs, set up Embassy space
- May '16: 12%
  - upload 82 images and data
  - set up main DB/Mart/NFS servers set up
- Jul '16: 25%
  - infrastructure devs: networking (route trafficking), security
  - shadowland ready
  - upload/testing e54/67 images (proof of concept)
- Aug '16: 40%
  - requisition enough compute/storage: 90GHz/344GB RAM/80TB
  - Sanger-EBI data migration (archive DBs/Mart/NFS)
- Sep '16: 60%
  - uploaded all archive/search instances
  - EBI-Embassy data transfer (martdb/nfs, ensdb 80%)
[Speaker Notes: Current rate: 5%/month, will end July 2016, but most of remaining are repeatable steps, infrastructure is in place, data transfer in place (need to fix couple of glitches and should be ok)]

---
FTP
- ~35TB disk: FTP, HTTP(S) and Rsync
  - mirrors depends on FTP (flat-files)
- EBI set up
  - 2 LB mirrored servers HH + HX (semi-auto) fail over, 75TB storage
  - covered by extra purchase
- Objective: migrate autumn 2016
[Speaker Notes: The Ensembl FTP site currently requires around 35TB of disk hosted on FTP , HTTP(S) and Rsync.]

---
FTP Migration Plan
- Requisition server/storage
- Test FUSE fs access
- Data transfer
- Release deployment procedures
- Switch DNS
[Speaker Notes: FUSE fs access for what? Release deployment procedures: sync process on a regular automatic cycle.]

---
Milestones (70%)
- Sep '15: 0%
  - pilot study into move
- Jan '16: 1%
  - request space (not available, need money)
- Apr '16: 5%
  - data transfer access point/ftp test server available
  - test transfer e!82-83
- July '16: 25%
  - FTP layout agreement, requisition server/storage
- Aug '16: 40%
  - internal beta testing available
  - service ready in HH, HX mount point
- Sep '16: 70%
  - data migration (shadowland)

---
Public MySQL
- Two servers cover all releases back to 24 (MySQL 4/5.1)
- GRCh37 server: e!79-86
- Objective: migrate autumn 2016
[Speaker Notes: We provide public access to our archived DBs with two MySQL servers covering all releases back to 24: one server handling MySQL4 (e!24-47) and a second handling 5.1 (e!48-present). In reality, we have underneath two sets of load balanced servers.]

---
Migration Plan
- Requisition HW/storage
- Copy DBs:
  - 1. 24-47
  - 2. 48-86
  - 3. GRCh37 79-86
- Backup strategy/SOP to push DBs to server per release
- Switch

---
Milestones (71%)
- May '16: 5%
  - HW procurement order
- Jul '16: 15%
  - warehouse available
- Aug '16: 50%
  - HW ready (not available)
  - data transfer (78TB, no e!86) to warehouse (shadowland)
- Sep '16: 70%
  - layout agreement (failover of public services on HH, backup, update)
  - HW available
- Oct '16: 71%
  - 86 DBs copied (www, grch37)

---
Production (incl. genebuild)
- Filesystems/storage:
  - 45 TB clustered (HX farm) + 200TB NFS long-term warehouse (lustre backup)
- Compute:
  - 500 CPU yrs (2015)	LSF farm
  - run genebuild/production Hive pipelines etc.
- Objective: run e!88 at EBI

---
Migration Plan
- Archive CVS
- Requisition HW/compute/storage
- Survive shutdown
- Software env
- Test pipelines@EBI
- Migrate warehouse, old DBs etc.

---
Milestones (State: 65%)
- Feb '16: 1%
  - clustered storage options/e! shared user
- Apr '16: 5%
  - software deps/install (RH6: perls, required libraries)
  - EBI cluster update to RH7!
  - Sanger CVS RO
- May '16: 15%
  - HW purchase
  - EBI farm minicourse
  - CVS at EBI (local co)
- Jun '16: 16%
  - RH7 software env (Andy) commence
    Sanger CVS turned off
- Jul '16: 40%
  - RH7 software area ready
  - farm storage/compute ready (100TB lustre/300TB warehouse)
- Aug '16: 55%
  - production HW ready
  - survived shutdown
  - pipelines tested (RH6)
- Sep '16: 65%
  - RH7 software env ready
  - HW available

---
Websites
- Services:
  - Core website (incl. Mart)
  - REST
  - Search
  - Accounts
  - Tools
  - Sessions
- www, AWS, GRCh37, e!g delivered from HH
- Objectives: migrate Q1 2017 (e!88)
  - infrastructure ready end 2016 (e!87)
[Speaker Notes: As for the websites, it's worth thinking of e! in terms of services. This is how they have been described to EBI TSC and how we'll be considering them in the future. Back in Sep there's been a meeting between the webteam and TSC to agree on the web topology and EBI deployment: failover between HH/HX, backups, replication between DCs. The majority of websites are delivered primarily from HH, but for each of them we need to consider whether the corresponding service is essential and needs to fail over to HX. Objective: should have some kind of live site running on EBI hardware by the end of 2016 to ensure any remaining kinks can be resolved quickly (especially if those kinks require additional hardware purchasing)]

---
Services (Core)
- 3 ro nfs volumes (localsw, 100GB pre-cached data, 10 TB datafiles)
- rw nfs for temp files
- rw sessions DB
- load balanced web/database servers
- dev environment
- email server

---
Services (Search)
- VMs (HH/HX)
- 500GB rw local disk
- 10GB rw temp space
- load balancing

---
Migration Plan
- Requisition HW
- Infrastructure for Tools framework
- Dev areas for web devs
- SOPs
  - test/live sites, search
  - post-release updates (data/code)
  - AWS
- Monitoring/notification/stats
  - define systems, transfer stats from Sanger
- Host in HH/HX
- Transfer domain
- Redirect DNS

---
Milestones (State: 21%)
- May '16: 5%
  - HW purchase
- Aug '16: 15%
  - HW ready
  - accounts/tools/hive DBs at EBI
  - survived shutdown
- Sep '16: 20%
  - web topology
  - defined dev env
  - dev MySQL server
  - e!86 DBs at EBI
- Oct '16: 21%
  - request prod Dbs, virtual users/project space

---
Overall: 55%
- Shutdown
- Infrastructure:
  - HW resources purchased/partly allocated (budget employed)
  - Networking infrastructure to support data transfer
- Public distribution:
  - Archives/FTP/public MySQL on the go (thanks to shadowland)
  - Web infrastructure work started (moved user/tools)
- Production:
  - HW requisitioned (DB servers, Farm, data storage)
  - CVS migrated
  - Long-term (RH7) software environment
- Outreach
  - RT migration to happen now

---
Acknowledgements
- Mag, Daniel
- Andy, Steve, Dan S^2
- Migration champions
- Group leaders
- Everybody in e!