Ensembl migration
The great (WTSI) e!scape
Alessandro Vullo
Ensembl Data Review
Oct 10 2016
EMBL – European Bioinformatics Institute
Wellcome Trust Genome Campus
Hinxton, Cambridge, CB10 1SD, UK

---
Objective(s)
assert(e_sanger_footprint == 0) if date =~ /Mar 2017/
  - maintenance of public face is of paramount importance: public web sites (HX/AWS), MySQL access, mailing lists
  - production processes are important but secondary

---
The Plan (Summary)
Migrate 3 groups in turn
  1. public archive services (archives, FTP/MySQL)/web presence (HX)
  2. release production processes
  3. processes outside of release cycle
[Speaker Notes: Expertise from Ensembl Genomes, who run many Ensembl pipelines already at EBI, will be leveraged. Early migration of non-release linked resources such as our archive and FTP site will ensure EBI is aware of our requirements and expose issues early. Maintenance of our public face is of paramount importance.]

---
Ensembl Flow
[Speaker Notes: How to think about e!? At the simplest level you distinguish two major areas: production/data release (web/FTP/MySQL) + helpdesk Ensembl operates a 4/5 release policy per year resulting in 9 releases over 2 years. This roughly means a production cycle and data release once every 11 weeks. During this production cycle (represented by Group 2 in Figure 1) data is delivered from content teams, processed by other content teams and then finally delivered to a staging database and file system depending on the data format. Once fully collated this data is delivered to our public distribution channels (represented by Group 3 in Figure 1) and mostly takes the form of 19 websites: one delivering the latest release and 16 delivering an archive release. The final Group represents data that is produced out of cycle and awaits the next Ensembl release to schedule further processing. For example a gene build, the process of annotating a genome with transcription models, is rarely released publicly without the addition of cross references and mappings between genome versions. The Vega website and data production tasks are the responsibility of the Ensembl webteam. This is generally done on a much smaller scale than, and at different times to, Ensembl. It does present a particular challenge in the need for frequent updates to data outside of the release cycle.]

---
Sanger Footprint
- ~330TB storage (production, web live/archive servers)
  - DDN 103TB
  - Nexsan 228TB
- ~110 machines: ? Cores/? RAM
  - ~30 production DB servers (BM)
  - ~80 web related servers (~50 BM/~30VMs)
  - RAM:
    - 1.1TB production
    - ? web (0.7TB DB, 1.7TB live/tools, ? archives)
  - Cores: ?
- Farm processing
  - ~500 CPU yrs (2015)
  - ~45 TB clustered filesystem (lustre)
  - ~200TB NFS storage areas (warehouse)
[Speaker Notes: The majority of Ensembl servers are bare metal. The exception are our archive web servers, search engines and private data (data sets which cannot be released externally) database servers which are VM based.]

---
3, 2, 1 go!
- September 2015: commence
- <February 2016: Ok-ish, slow pace
  - initial discussions with EBI/Sanger groups
  - AV takes on PM role (Jan)
  - identify tech requirements in more details
    - benchmarking Sanger machines: mainly storage
    - DB meetings (move data across, back ups, MySQL versions)
- Feb 2016: shutdown in HX, bang!

---
Hinxton Data Centre Shutdown
- 26-30 Aug 2016, power cycle (every 5 yrs), electrical maintenance
- Impact: internal/external services HX hosted
- Major consequences for e!

---
Oh no, suicidal!
- Some production/web db servers on potentially faulty IBM blades (50% chance to recover)
- No strategy other than Sanger/IBM try to fix them
- Sanger suggests to migrate away from this HW ASAP!
- Main concerns:
  - managing release
  - guarantee public services

---
We need HW soon!
- Cope with shutdown, provision in time to advance plan implementation
- Need ~£400K hypevisors/storage
- Have ~£250K (e! overhang budget)
- Will:
  - buy in on e! budget (£150K shortfall)
  - EBI pre-award push shortfall into
  - WT award in Oct charged EMBL pre-award

---
Strategy (web)
- user/tools/hive DBs migrate to EBI asap
- fast private direct link Sanger-EBI (shadowland) connects web/archives to DBs
- EBI-AWS VPN for mirrors
- Sanger blades:
  - web servers OK
  - species/mart/other DBs are suicidal, use Solr servers as fallback (not very performant)

---
Strategy (production)
- production remains at Sanger
  - e!86 processes finish before (Aug 22)
- staging servers backed up
- teams (i.e. genebuild) make sure not to use suicidal HW
- suicidal servers flagged for attention
  - source suitable replacements if problems

---
Web & VPN/shadowland

---
What Happened
- A number of VMWare VMs have come back with different IPs
- Pb with new Solr servers, java process stopping e! tomcat
- A number of the IBM blades have not come back and some others had trouble with their storage
  - new system board and more memory
  - All blades back and serviceable (Aug 31 evening)

---
Public Archive Services
- e! maintains archive of past releases (3ys)
  - past 13 (includes NCBI36 e!54), e.g. may2009.archive.ensembl.org
  - 2 key species archive: NCBI m37 (e67), Zv8 (e59)?
- Objective: migrate autumn/fall 2016
[Speaker Notes: In the next WT funding cycle this will grow to 5 years of archives. We will aim to migrate our public archive services first followed by our public web presence (group 3). Early migration of non-release linked resources such as our archive and FTP site will ensure EBI is aware of our requirements and expose issues early.]

---
WTSI set up

---
WTSI set up (2)
- 28 servers: ? Cores/? RAM/? storage
  - 15 releases archive (past 13 releases plus 2 key species plus GRCh37): 18 VMs, ? Cores/? GB RAM/Storage?
  - Each archive site accompanied by search server: 15VMs, ? Cores /225GB RAM/7TB DDN
    - 8 Solr e!>=73
    - 5 Lucene
    - 1 exalead
  - Archives/GRCh37 DB-Solr servers: ? Cores/? RAM/? Storage (BM)
  - NFS? Web data
  - Shared user DB with live web
  - Hosted on VMWare virtualisation platform

---
Archives Migration Plan
- Spring 2016 – Migrate 82 archive (WP1) (not full fledge migration, need completion of WP2 before run)
  - request image
  - requisition DB servers (data hosting, user sessions, mart)/NFS server
  - copy release data from EBI mirror
  - upload WTSI images (web/solr search) – critical

---
Archives Migration Plan (2)
- Autumn 2016 – Host all archives on Embassy (why?) (WP2)
  - transfer all images
  - EBI-Embassy VPN (shared accounts DB)
  - deploy service monitoring infrastructure
  - control procedures/load balancer
  - transfer stats
  - switch DNS

---
Milestones
State: 60% done
- Jan 2016: 1%
  - request 82 Vms, set up Embassy space
- March-May 2016: 5%
  - upload 82 images (ovftool from Sanger farm) and data (EBI mirror)
  - main DB/Mart/NFS servers set up, (temp accounts DB replacement)
- June 2016: 10%
  - infrastructure developments: networking (route trafficking), security
- July 2016: 25%
  - shadowland ready for data transferring
  - upload/testing e54/67 images (proof of concept)
- August 2016: 60%
  - requisition enough compute/storage: 90GHz/200GB RAM/80TB
  - data migration (archive DBs/Mart/NFS)
[Speaker Notes: Current rate: 5%/month, will end July 2016, but most of remaining are repeatable steps, infrastructure is in place, data transfer in place (need to fix couple of glitches and should be ok)]

---
FTP
- 32TB disk hosted on FTP, HTTP(S) and Rsync
  - mirrors depends on FTP (flat-files)
- require to be able to sync, on a per release basis, all data held in the Ensembl FTP site onto a co-mirror hosted in HH
- EBI set up
  - 2 LB mirrored servers HH + HX (semi-auto) fail over, 75TB storage
  - covered by extra purchase
- Objective: migrate by end 2016

---
FTP Migration Plan
- Requisition server/storage
- Test FTP/FUSE fs access
- Data transfer
- Release deployment procedures
- Switch DNS

---
Milestones
State: 50%
- Sep 2015: 0%
  - pilot study into move
- January 2016: 1%
  - request space (not available, need money)
- April 2016: 5%
  - data transfer access point/ftp test server available
  - test transfer e!82-83
- July 2016: 25%
  - FTP layout agreement, requisition server/storage
- August 2016: 30%
  - internal beta testing available
- September 2016: 50%?
  - data migration (shadowland)

---
Public MySQL
- Two servers cover all releases back to 24 (MySQL 4/5.1)
  - note on MySQL versions?
- GRCh37 set up?
- Objective: migrate fall 2016

---
Migration Plan
- Copy DBs:
  - 1. 24-47, then host
  - 2. 48-present, then host
  - 3. GRCh37 79-present, then host
- Requisition HW/storage
- Develop SOP to push DBs to server per release
- Sync/Switch DNS

---
Milestones
State: 70% done
- May 2016: 30%
  - HW procurement order
- August 2016: 70%
  - HW available
  - investigate failover of public services on HH
  - copy all releases to warehouse (shadowland)

---
Production (including genebuild)
- Filesystems/storage:
  - 45 TB clustered (HX farm) + 200TB NFS long-term warehouse (lustre backup)
- Compute:
  - 500 CPU yrs (2015)	LSF farm
  - run genebuild/production Hive pipelines etc.
- Objective: migrate after web (Q1 2017)

---
Migration Plan
- Migrate CVS
- Requisition compute/storage
- Test pipelines EBI
- Release build process survives shutdown
- Migrate pipelines/warehouse

---
Milestones
State: 70% done
- Feb 2016: 1%
  - Clustered storage options/e! shared user
- April 2016: 5%
  - software installations (perl, pipeline dependencies)
  - EBI cluster update to RH7!
- June 2016: 15%
  - EBI farm minicourse
  - work on RH7 software environment (Andy)
- July 2016: 50%
  - farm storage/compute ready
- August 2016: 65%
  - production HW ready (after shutdown)
  - shutdown?
  - RH7 software env/area ready

---
Live e! Websites
- Dialogue with Steve to figure out the whole infrastructure and describe it in a simple but detailed way
- Storage, compute (web/farm nodes), filesystems
- Objectives: should have some kind of live site running on EBI hardware by the end of 2016 to ensure any remaining kinks can be resolved quickly (especially if those kinks require additional hardware purchasing)

---
Migration Plan

---
Milestones

---
Overall
State: ~60%?
- (Gracefully) survived shutdown (?)
- Infrastructure:
  - HW resources purchased/partly allocated (budget employed, accountancy wizardry)
  - Networking infrastructure to support data transfer
- Public distribution:
  - Archives/FTP/public MySQL on the go (thanks to shadowland)
  - Web infrastructure work started (moved user/tools)
- Production:
  - HW requisitioned (DB servers, Farm, data storage)
  - CVS migrated
  - software environment installed (almost stabilised), pipelines tested
- Outreach
  - RT migrated?

---
Acknowledgements
- Mag, Daniel
  - supportive and guiding in difficult moments
- Andy, Steve, Dan Ss
  - the underlying heroes, competent gentlemen
- Migration champions
- Group leaders
- Everybody in e!